## Sheet1
Richmond Free Library
Capital Expenditures & Maintnenance Planning Document
Updated February 7 2025
Project | Funding Source(s_ | Description | Cost Estimate | FY | NOTES
Water problems | Town of Richmond | Develop a plan to correct water issues around sill plate, concrete and entry door as well as path of water from eaves to canopy and running down siding. There are questions about proper flashing behind concrete and the impact of the vapor barrier in the basement. These issues are now impacting the ability of the door to function properly, in addition to rotting sill plate and siding. |  | FY25 | Jay Labare recommends contacting an architect to determine the proper solution and draft construction documents. We are working to find 3 bidders
Bridge Street (historic) Front Door | Library Reserve | Weatherization work around historic front door and windows in community room. Efficiency Vermont came and looked at problem, made recommendations. |  | FY25 | Getting a recommendation for contractors to bid from Efficiency Vermont
Pest Control | Library Maintenance | Fal & spring pest sprays and rodenticide montlly -- received 3 bids | $900 annual | FY25 | DONE Erlich low bidder
Pest Control | Town of Richmond | Seal up exterior of building against rodents - received 3 bids | $500 one time | FY25 | DONE Erlich low bidder
Bats | Town of Richmond | Contacting Bats in the Belfrey and one other company to explore how to eliminate bats who are nesting in belfrey. |  | FY25
Sidewalk | Town of Richmond | Handicap sidewalk and steps to parking lot from Bridge Street have been patched and patched. For liability reasons, this needs to be repaired. |  | FY25 | Could this be done by Town Crew?
Roof | DOL Grant, Fundraising or Town of Richmond | Slate roofs typically last 150 years, as of 2024 we are beyond 150 years. We based on inspections we have 2 options |  |  | Apply for DOL grant
| Option #1 | Fully Replace Roof | 280000
| Option #2 | Replace damaged shingles on a schedule of every 3-4 years | 128000 |  | First year cost, subsequent years should be less
Front Steps | Town of Richmond | Front masonery steps have been repaired 3 times. They do not meet code. Historic restoration to same configuration refacing with stone to match foundation. | 82500 |  | Grant application not successful
Carpets | Library Reserve | Existing carpets need to be cleaned | 1200 | FY26
Interior painting | Library Reserve | Interior of community room and remainder of first floor stacks. |  | FY26
Refinish floor | Library Reserve | Refinish floor of Community Room | $2,500-$6,000 | FY27
Lighting | Library Reserve | Old ballasts are being replaced with LED lighting as they fail. | Costs absorbed into Maintnenance budget
Boiler | Library Reserve | Boiler life is unknown at this time | Will ask NEA to give us an assessment
Projects Recently Completed
Flooring | Library Reserve | Replaced first floor entry and tech room and 2 upstais bathrooms flooring |  | FY25
Painting | Town of Richmond | Fully scraped, repaired and repainted |  | FY25 | ARPA
Wood Repair | Town of Richmond | Repair of wood siding, trim and sillplate |  | FY24 | Grant & Town
Restoration | Town of Richmond | 5 historic windows restored |  | FY24 | Grant & Town
Tree Trimming | Town of Richmond | As proposed by Tree Warden |  | FY 24 | Town